## Sheet2
| Task | Overall Flow | Output
2020-01-03 | 1) Individual EDA for test, train, weather, spray (Le-Anne, Shawn) 2) Visualisation of spray data by location (Jiansheng) | EDA | Identify data to be cleaned and possible relation between data sets
2020-01-04 | 1) Team to discuss findings from individual EDA 2)Data Cleaning and Feature Engineering (All) | EDA
2020-01-05 | Data Cleaning and Feature Engineering (All) | EDA
2020-01-06 | 1) Team to discuss data set and modeling approach | EDA / Additional Research | Cleaned data used for modeling
2020-01-07 | 1) Merge Data Set for Model (Shawn) 2) Create Models, read up on over-sampling, SMOTE and Tomek (Le-Anne) 3)Explore use of folium (Jiansheng) | Additional Research / Exploration
2020-01-08 | 1) Explore Features with Various Models 2) Research on WNV and spray costs | Additional Research / Exploration
2020-01-09 | 1) Explore Features with Various Models 2) Research on WNV and spray costs | Modeling / Additional Feature Engineering | Additional Features Generated for Model
2020-01-10 | Modelling and Additional Feature Engineering | Modeling | Visualisation on Spray Data and num of mosquito
2020-01-11 | 1) Model Selection 2) Team to discuss approach for CBA and recommendations | Modeling | Final Model to be selected
2020-01-12 | 1) Visualisation of Predictions on map 2) Discuss CBA approach | CBA | Predicted probabilties for WNV presence and combine data with latitude/longitude
2020-01-13 | 1) Cost Benefit Analysis 2) Presentation Slides | CBA | Proposal for pesticides Presentation Slides
2020-01-14 | Presentation